## Measurement form
Bill of Quantities
SL# | Voltage level(kV) | Clearance requirement | Location | Approx. Line Length (km) | Rate [Nu] | Amount [Nu] | Remarks
1 | 33 | Clearing of all growth (inclusive of bushes and creepers) within 6.0Mtr from the center line on both the side (12Mtrs in total) and in addition, trees (upper side of the line) that could fall and contact the line | Thunwa, Ranitar, Herintar, Jigme Singye Wangchuk,Sanglung, Sengdhen, Dorokha, Denchukha, Dumtoe, Basanti, Mithun, Sebichang and part of Rangtse village | 142 |  |  | Payment will be made as per actual work done
|  |  | Samtse, Bastar, Duarpani, Lamitar, Uttary and Phuentshoelri | 15
|  |  | Dhamdum to Tashichhoeling, Jogimara to Tashichhoeling | 37
|  |  | Total 33kV line (km) | 194
2 | 11 | Clearing of all growth (inclusive of bushes and creepers) within 4.5Mtr from center line on both the side (9Mtrs in total) and in addition, trees (upper side of the line) that could fall and contact the line | Tading | 7
|  |  | Samtse, Norbugang, Ugyentse, Phuntshopelri and Parts of Sangacholing Gewog | 202
|  |  | Tashichhoeling, Namgaychhoeling, Pemaling, Tendruk, Norgaygang and parts of Sangachhoeling Gewog | 248
|  |  | Total 11kV line (km) | 457
Total Amount [Nu]

## Schedule (2)
Schedule for Tender
Date
SL# | Description | From | To
1 | Sale of Tender | 16.01.2020 | 15.02.2020 | 30 Days
2 | Opening of Tender | 15.02.2020 | 3PM |  | Feb | March | April | May | June
3 | Bid Validity |  | 90 days after bid opening |  | 14 | 31 | 30 | 15
4 | Bid security | 16.02.2020 | 30 days beyond bid validity |  |  |  |  | 16 | 14
5

## Estimate
Estimate for RoW
SL# | Voltage level(kV) | Clearance requirement | Location | Line Length (km) | Rate(Nu) | Total Amount
1 | 33 | Clearing of all growth ( inclusive of bushes and creepers) within 6.0Mtr of the center line on both the side ( 12Mtrs) and in addition, of the trees that could fall and contact the line | Dhamdum to Dorokha-Wangchuk under Dorokha Drungkhag | 57
|  |  | Dhamdum to Ugyentse | 12
|  |  | Total 33kV line (km) | 69 | 7000 | 483000 | 275931 | 42.87%
2 | 11 | Clearing of all growth ( inclusive of bushes and creepers) within 4.5Mtr of the center line on both the side ( 12Mtrs) and in addition, of the trees that could fall and contact the line | Sarkikhola - Suktey-Boteykharka | 7.01 |  |  | 42.87%
|  |  | Alay Sangla- Sinkauley | 10.5
|  |  | Gawadong-Kalingtar | 4.2
|  |  | Samtse -Sang-Nga-Chholing | 32.5
|  |  | Samtse -Dhamdum | 6.4
|  |  | Tashchholing -Norgaygang | 31.54
|  |  | Upper Talay- Puridara and Jamirkot area | 9.62
|  |  | Total 11kV line (km) | 101.77 | 6500 | 661505 | 406978.23 | 38.48%
|  |  | Total |  |  | 1144505 | 38.48%
|  |  | Bid Security |  |  | 22890.1
682909.23
461595.77
228901
|  |  | 20% of contract price | 136581.846 |  | 232694.77

## Schedule
Schedule for Tender
Date
SL# | Description | From | To
1 | Sale of Tender | 16.01.2020 | 15.02.2020 | 30 Days
2 | Opening of Tender | 15.02.2020 | 3PM
3 | Evaluation of Tender | 16.02.2020 | 18.02.2020
4 | Presentation of tender evaluation report | 24.02.2020
5 | Issuance of Letter of Intend to Award | 24.02.2020 |  | 3 working days
6 | Issuance of Notification of Award | 01.03.2020
7 | Received of letter of acceptance | 01.03.2020
8 | Submission of performance security by Bidder and Signing of Contract Agreement | 04.03.2020 |  | within 3 working days
9 | Issuance of work order | 04.03.2020
10 | Handing taking of Site | 05.03.2020 |  |  | March | April | May
11 | Work Completion |  |  |  | 27 | 30 | 3

## tender opening member
Proposed tender opening committee
SL# | Name | Remarks
1 | Mr. Vesraj | Chair person
2 | Mr. Uttam Sunar | member
3 | Mr. Yeshila | member
4 | Mr. Robin Gurung | Finance

## Tender Evaluation memeber
Proposed Tender Evaluation committee
SL# | Name | Remarks
1 | Ms.Kunzang Pemo | Team leader
2 | Mr. Thinley Namgay | member
3 | Mr. Robin Gurung | member